## Test Plan
TEST PLAN — E-Commerce Manual Testing Project
Application: nopCommerce Demo Store ¦ Version: 1.0 ¦ Author: Ali Ennadafy ¦ Date: February 2026
1. PROJECT OVERVIEW
Project Name | E-Commerce Manual Testing Project — nopCommerce Demo Store
Application URL | https://demo.nopcommerce.com/
Testing Type | Manual Functional Testing, Security Testing, UI/UX Testing, Boundary Testing
Author | Ali Ennadafy — Manual QA Engineer
Start Date | 01 February 2026
End Date | 22 March 2026
Document Version | v1.0 — Final
2. TEST OBJECTIVES
• Validate all core e-commerce user flows: Registration, Login, Product Browsing, Cart, Checkout, Orders, and User Profile • Verify authentication and session management security controls • Identify functional defects, boundary violations, and security vulnerabilities • Ensure business logic correctness (pricing, discounts, order processing) • Produce professional QA documentation for portfolio demonstration
3. TEST SCOPE
Module | In Scope | Out of Scope | Out of Scope
Registration | Field validation, Email format, Password rules, Duplicate accounts |  | Backend API internals, Database schema
Login / Logout | Valid/invalid credentials, Session management, Multi-tab behavior |  | OAuth integration, Social login
Product Listing | Page load, Product data, Sorting, Filtering, Pagination |  | Product catalog management (admin)
Product Details | Product info display, Image, Zoom, Add to Cart |  | Product reviews submission flow
Search & Filter | Keyword search, Category & manufacturer filters |  | Search engine indexing
Shopping Cart | Add/update/remove products, Cart persistence |  | Coupon/voucher codes
Checkout | Billing address, Shipping method, Payment selection |  | Actual payment processing
Order Confirmation | Success message, Order number, Order details link |  | Email notification delivery
Order History | Order list display, Order details, Pagination |  | Order cancellation/returns
User Profile | Edit profile, Change password, Address management, Security |  | Admin user management
4. TEST ENVIRONMENT
Application | nopCommerce Demo Store — https://demo.nopcommerce.com/
Browser | Google Chrome (Latest Version)
Operating System | Windows 10 (64-bit)
Tools | Microsoft Excel (Test Cases & Bug Reports), Chrome DevTools (Debugging)
Network | Standard WiFi Connection (~10 Mbps)
Devices | Desktop PC
Test Data | Test accounts created on nopCommerce demo environment. No real payment or personal data used.
5. TEST STRATEGY & APPROACH
Testing Techniques Applied: • Boundary Value Analysis (BVA): Testing minimum, maximum, and just-outside values for input fields. • Equivalence Partitioning (EP): Grouping inputs into valid/invalid partitions to reduce redundancy. • Negative Testing: Verifying system behavior with invalid, empty, or unexpected inputs. • Error Guessing: Using experience to identify likely failure points (edge cases). • Session & Security Testing: Verifying authentication flows, session invalidation, and access control. • UI/UX Testing: Checking visual consistency, accessibility, and usability across pages. Test Execution Order: Follows the natural user journey — Registration → Login → Product Browsing → Cart → Checkout → Orders → Profile.
6. RISK ANALYSIS
Risk ID | Risk Description | Impact | Likelihood | Mitigation
R-001 | Demo environment may reset or be unavailable | High | Medium | Run tests daily and document results immediately
R-002 | Limited products in demo may block pagination testing | Medium | High | Mark affected TCs as 'Not Applicable' and document
R-003 | No real payment processing possible in demo | High | Certain | Test up to order placement only; document limitation
R-004 | Session timeout may be disabled in demo | High | High | Document findings and mark as defect
R-005 | Demo data may be shared/reset by other users | Medium | Medium | Re-create test data before each session
7. ENTRY & EXIT CRITERIA
Entry Criteria | • Test environment (nopCommerce demo) is accessible • Test cases are documented and reviewed • Test data (user accounts) are created • Browser is configured and DevTools accessible
Exit Criteria | • All planned test cases have been executed • All critical/high defects are documented • Test Summary Report is completed • Pass rate ≥ 85% for high-priority modules • All findings are logged and traceable
8. TEST DELIVERABLES
Deliverable | Description
Test Plan | This document — Test Plan (Excel) |  |  |  | ✅ Completed
Test Cases | Excel files per module (12 modules) |  |  |  | ✅ Completed
Bug Reports | Excel files per module with defect details |  |  |  | ✅ Completed
Test Summary Report | Complete test summary with pass rates and defects |  |  |  | ✅ Completed
RTM | Requirement Traceability Matrix (Excel) |  |  |  | ✅ Completed
API Testing (Postman) | Postman collection with test scripts |  |  |  | 🔄 In Progress
Automation Framework | Selenium/Python test automation (future) |  |  |  | ⏳ Planned